## ASUC Closing FY22
B&F FISCAL YEAR CLOSING SCHEDULE/CHECKLIST
Type of Action
Revised 06/22/2022
RESPONSIBLE PARTY | DATE DUE | DAY DUE | TIME DUE | System/Category | FISCAL CLOSING STEP
Financial Requestor | 2022-06-30 | Thursday | 12:00 | CalLink | Last day to submit FY 21-22 purchase orders, reimbursements, check requests and vendor invoices to B&F AP Office. Please note in Stage Comments that this is from FY 21-22.
Financial Requestor | 2022-07-01 | Friday | N/A | CalLink | Begin submitting FY 22-23 CalLink requests to B&F AP Office. Check service date to ensure expense is for FY 22-23. Comment on CalLink when Stage 5. If service date is for FY 21-22, contact the Business & Finance Office.
LEAD | 2022-07-15 | Friday | COB | Google sheet | Last day to submit any accruals (>$2,000), corrections, or adjustments to Business & Finance (B&F) Office for inclusion in the June financial reports.
LEAD, CFO and VPoF | 2022-07-29 | Friday | COB | Email | Last day to submit any exceptional carry forward or budget allocation requests to B&F Office.
Orgs, Lead, and B&F | 2022-06-30 | Thursday | 10:30am | Check and Cash with Deposit Form | Last day to submit deposits to B&F AP Office for deposit to Union Bank. Deposits received by B&F AP Office after the 06/30/22 deadline will be posted to the FY22 ledger in CalLink.
SU Finance | 2022-06-24 | Friday | COB | MIP | May financial reports posted to Google drive by B&F Office.
SU Finance | 2022-06-30 | Thursday | COB | MIP | B&F Office sets up new fiscal year in MIP.
SU Finance | 2022-06-30 | Thursday | COB | Bank Deposit | Deposits made to Union Bank by B&F AP Office.
SU Finance | 2022-07-08 | Friday | COB | MIP | B&F Office completes any corrections or adjustments for the May financial reports.
SU Finance | 2022-07-08 | Friday | COB | Invoice | ASUC SU B&F invoices ASUC and GA for any outstanding expenses as of 06/30/2022 for Dept IDs 30344, 30341, and 21331; plus any RSO-related Event Services invoices
SU Finance | 2022-07-08 | Friday | COB | Invoice | Pass Thru review and billing for Dept ID 21335
SU Finance | 2022-07-08 | Friday | N/A | CalLink | B&F AP Office begins review of all incoming CalLink requests. New fiscal year requests are separated from previous fiscal year requests.
SU Finance | 2022-07-15 | Friday | COB | MIP | B&F AP office processes final AP transactions for all other FY21-22 payments using 06/30/22 business date.
SU Finance | 2022-07-15 | Friday | COB | CalLink and MIP | B&F AP Office completes reconciliation of all outstanding encumbrances and closes out all remaining outstanding POs with final invoices
SU Finance | 2022-07-15 | Friday | N/A | CalLink | B&F Office begins review of CalLink requests. Requests will proceed to Stage 5, but will not yet be approved in CalLink.
SU Finance | 2022-07-19 | Tuesday | COB | MIP | B&F Office completes any accruals, corrections, or adjustments for the June financial reports.
SU Finance | 2022-07-22 | Friday | COB | MIP | June preliminary financial reports posted to Google drive by B&F Office.
SU Finance | 2022-08-01 | Monday | COB | CalLink and MIP | B&F AP Office completes PO cancellation requests. B&F AP Office reviews all open encumbrances and closes all POs in MIP for current fiscal year.
SU Finance | 2022-08-01 | Monday | N/A | CalLink | 7/1/22, B&F begins to cancel prior year requests in Callink (FY21 and previous)
SU Finance | 2022-08-05 | Friday | COB | CalLink | B&F Office completes and uploads CalLink worksheet to clear FY21-22 balances, add the FY22-23 Budget, and add the FY21-22 carry forward.
SU Finance | 2022-08-10 | Wed | COB | MIP | B&F Office runs final June reports for retention.
SU Finance | 2022-08-10 | Wed | COB | CalLink and MIP | B&F Office completes any exceptional FY 21/22 Carry Forward and FY 22/23 Budget Allocation
SU Finance | 2022-08-15 | Monday | N/A | CalLink | FY 22/23 CalLink begins
SU Finance | 2022-08-15 | Monday | N/A | CalLink | FY 22/23 year begins, start 8/15 go back to CalLink & approve all FY 22/23 approved CalLink requests since 7/1/22. Do deposit upload & checks attachements.
SU Finance | 2022-08-16 | Tuesday | COB | MIP | B&F Office prepares prior fiscal year carryforward journal in MIP to current fiscal year. Journal auto reverses in new fiscal year.
SU Finance | 2022-08-16 | Tuesday | COB | Office Application | B&F Office prepares and sends letter to the ASUC and GA for current fiscal year Student Services Fees.
SU Finance | 2022-08-19 | Friday | COB | MIP | B&F Office processes year end investment account closing in MIP.
SU Finance | 2022-08-19 | Friday | COB | Fund Balances | B&F Office prepares and sends letters to ASUC and GA regarding the preliminary funds balances from the prior fiscal year.
SU Finance | 2022-08-26 | Friday | COB | bCal | B&F prepares notification to send to appropriate GA and ASUC officials for MIP report training appointment
SU Finance | 2022-08-26 | Friday | COB | Email | B&F Office contacts Mah & Associates to set up the schedule for the audit.
SU Finance | 2022-08-26 | Friday | COB | Invoice | Invoicing ASUC Student Union for the 250K
SU Finance | 8/1/22-8/5/22 |  | N/A | CalLink | CalLink "DEAD PERIOD": All activity in CalLink suspended while finalizing end-of-year 21-22 account balances. Create csv files for record keeping. Will not zero out balances in phases: GA/GOVT/SISG/PUB/SAG because we are creating new chart of accounts on CalLink that matches with new chart of accounts on MIP.
VPof and CFO | 2022-07-01 | Friday | COB | Email | Last day to submit any corrections or adjustments to Business & Finance (B&F) Office for inclusion in the May financial reports.